## Issue Log
Item# | Date | Reported by | Issue description | Bug VS. Enhancement | ETA | Completed Date | Assigned to | Dev Complete | QA Complete | UAT Complete | Status | Notes/ Ticket #
1 | 2025-05-07 | Gerri | Demo of selecting "Next Gen" cycle count from main page in SB. Legacy - removed after all locatons have migrated. |  |  |  | Raghu |  |  |  | Resolved
2 | 2025-05-07 | Raghu | Provide SB IDs for testing location(s) |  | 2025-05-14 | 2025-05-12 | Gerri |  |  |  | Resolved
3 | 2025-05-07 | Raghu | Example of cycle count with file name/format. Coding completed. Working on testing Added to test case 6/11 - Output is still showing serials in wrong format. Added to chat. Gerri 6/16 - Review with TCP team; updates later this week - Gerri |  | 2025-07-23 |  | Garima |  | ` |  | Resolved | SBXA-15808- In QA and ready for testing Need to retest - UAT PIV test needed to confirm all looks well in production. mirror legacy format of file;
4 | 2025-05-07 | Gerri | RMA portal for discrepancy label reprint. How does field distinguish between RMA vs. Cycle count discrepancy label. RMA Type Raghu investigating - 5/27 Change to pass to shipping Gateway 6/16 - Raghu t0 add ticket number |  |  |  | Raghu |  |  |  | Resolved | SBXA-15881
5 | 2025-05-07 | Gerri | Demo of TCP consolidation process Understand how they pull all files from mailbox and compile for reporting. |  | 2025-05-13 |  | Gerri |  |  |  | Resolved
6 | 2025-05-07 | Gerri | Change verbiage for different "Overages" EX: Installed, DOA, unknown Gerri to add to test cases - In progress - New column added to Matrix 6/16 - Looking for more examples - Gerri |  | tbd |  | Gerri |  |  |  | In Progress | Waiting on retest due to verbiage; Raghu and Padma In progress until testing complete
7 | 2025-05-12 | Gerri | Shipping label/packing slip requirements for TLC Receiving sorting process Katie confirmed - "TLC - SUR Cycle Count Discrepancies" - 5/27 |  |  |  | Gerri |  |  |  | Resolved
8 | 2025-05-20 | Gerri | Need data for testing in QA Raghu shared logins for 2 testing accounts (ATT/3PL) RMA Portal added to both logins - 6/10 Datazap required - 6/2 |  |  |  | Raghu |  |  |  | Resolved | SBXA-15882
9 | 2025-05-19 | Raghu | Added Terminal Statuses Integrity team uses to Martix EX: Lost-Cycle Count New enhancement - Requires Dev work 6/16 - Raghu to update with ticket |  |  |  | Garima |  |  |  | Resolved | SBXA-15836
10 | 2025-05-21 | Garima | Confirm which location will be used in QA - Garima to check data Follow up with Raghu, Gerri and Garima |  |  |  | Raghu/Garima |  |  |  | Resolved | SBXA-15835
11 | 2025-05-21 | Kelly | Test cases - Truth Table 6/16 -- Second separate meeting with Raghu, Garima, Gerri - review cases, any additional information needed |  | TBD |  | Gerri |  |  |  | In Progress | 70% complete; continuing research In progress until testing complete
12 | 2025-05-27 | Gerri | NEW - Remove "FSL" from export file in columns (G/H) FSL In Stock Qty FSL Available Qty Code change needed 6/16 -- Code change is done; Raghu will provide update |  |  |  | Garima |  |  |  | Resolved | /SBXA-15906
14 | 2025-05-27 | Gerri | NEW - Send Raghu example of "Expected Return" serials for review |  |  |  | Gerri |  |  |  | Resolved | SBXA-15886
15 | 2025-05-27 | Gerri | NEW - Confirm serial in final count shows full serial vs. format issue with extra zeros |  |  |  | Garima |  |  |  | Resolved
16 | 2025-05-29 | Gerri | NEW - Send Raghu example of discrepancy/current status example for testing. Data zap required to upload different scenarios for testing. Updated Matrix 5/30 |  |  |  | Gerri |  |  |  | Resolved
17 | 2025-05-29 | Gerri | Garima to send Gerri list of SCM Actions for Matrix |  | 2025-06-03 |  | Garima |  |  |  | Resolved | SBXA-15896
18 | 2025-06-02 | Gerri | NEW - Change error message to red for unknown parts. Raghu to confirm 6/16/ -- Ticket has been opened to confirm. Raghu will provide update |  |  |  | Raghu |  |  |  | Resolved | SBXA-15882
19 | 2025-06-02 | Gerri | NEW - Will the UI have sounds for each scan? There are 2 sounds in Legacy ( error/overages/scanning serial twice) Confirmed NextGen has sound for errors, scanning serial twice 6/16/ -- Ticket requested -- back log, prioritization |  |  |  | Raghu |  |  |  | Resolved | SBXA-15883- In QA and ready for testing Gerri to do a screen recording to show display the sound.
20 | 2025-06-02 | Gerri | NEW - Add SCM Action "Return through DOA/Core process" - See Matrix for details 6/16 -- Ticket in progress - Raghu |  |  |  | Garima |  |  | 2025-07-08 | Resolved | SBXA-15835
21 | 2025-06-02 | Gerri | Scenario #41 - Duplicate serial in current status 6/16 - Raghu to investigate |  |  |  | Raghu |  |  |  | Resolved | This is data issue and bug in existing cycle count.
22 | 2025-06-04 | Gerri | Confirm if cycle counts automatically close at midnight. YES | [7 empty] | Resolved
23 | 2025-06-04 | Gerri | Summary tab to mirror Legacy format. In NextGen the field has to save and exit to see the summary every time they want to review what's missing. 6/16 -- Raghu - investigating and will provide update |  |  |  | Raghu |  |  |  | Resolved | SBXA-15884
24 | 2025-06-04 | Gerri | Ability to export cycle count in preview report screen 6/16 -- Raghu - investigate possibilities such as sortable, ability to search 7/25 - Confirmed ability to export preview report. Gerri |  |  |  | Raghu |  |  |  | In Progress | /SBXA-15906 - In QA and ready for testing 7/16: need to retest 7/24: Gerri to reconfirm; get screenshots 7/28: preview report not showing in email like it does for Candyland 8/11: verbiage change needed. Match Candyland 8/18: still under review and not in QA yet
25 | 2025-06-05 | Gerri | Is there a character limitation for notes. 250 limit SB support needed to investigate/fix in Legacy | [7 empty] | Resolved
26 | 2025-06-06 | Gerri | Testing - non serialized part scanned in nonserialized tab. showing record as unknown in serialized parts with action as RETURN Will unexpected nonserialized parts show in serialized tab? 6/16 -- this has been resolved for now |  |  |  | Garima |  |  |  | Resolved
27 | 2025-06-06 | Gerri | Testing - When clicking decrement or clear, the qty scanned didn't change for non-serialized part and shows message below. Field needs ability to change qty in case of misscan Error message when "Part scanned. Ensure qty scanned is accurate before completing cycle count" 6/16 - Raghu added Ticket |  |  |  | Raghu |  |  | 2025-07-08 | Resolved | SBXA-15886- In QA and ready for testing
28 | 2025-06-06 | Raghu | Fill in discrepancy status for NextGen. Raghu will provide ETA for testing. 6/16 -- Raghu - in progress; Gerri has a few left to enter |  |  |  | Gerri |  |  |  | Resolved
29 | 2025-06-06 | Gerri | Need final cycle report from AT&T testing location to review output. Count completed 6/4. Next Gen not showing export link. Raghu investigating -0058141 /78839372 - Gerri credentials showing invalid 6/16 -- Raghu -- still testing; to provide updates |  |  |  | Raghu |  |  |  | Resolved | the email will provide a link to save the report. No need to login to the cycle count application
30 | 2025-06-07 | Gerri | For any unknown part or mis-scan change error message verbiage. See test case# |  | 2025-07-29 |  | Raghu |  |  | 2025-07-30 | Resolved | In QA and ready to test Gerri confirmed 7/30/25 Serialized "The serial or part scanned is not recognized. Please return at the end of the cycle count." Random misscan "No quantity counted, please investigate and ensure part was not missed during cycle count."
31 | 2025-06-13 | Gerri | Add warning message for User to confirm they want to submit final count. Mirror Legacy 6/16 -- Raghu - ticket submitted for code changes 7/8 - Gerri confirmed it's visible in QA |  |  |  | Raghu |  |  | 2025-07-08 | Resolved | SBXA-15896- In QA and ready to test
32 | 2025-06-13 | Gerri | Confirm if notes entered will be visible as "Saved Notes" so field can confirm all required notes were entered correctly. 6/16 -- Raghu - ticket submitted for code changes. Padma created new CR for adding new column to show saved notes SBXA-16161 | enhancement SBXA-16161 |  |  | Raghu |  |  |  | Resolved | SBXA-16161 needs to be prioritized as enhancement
33 | 2025-06-13 | Gerri | Understand why UI won't allow notes to be entered for non-serialized parts in preview screen. Need ability to enter notes for all lines 6/16 -- Raghu - ticket submitted for code changes 7/8 - Gerri confirmed field can add notes to any line item in QA (preview screen) |  |  |  | Raghu |  |  | 2025-07-08 | Resolved | SBXA-15892
34 | 2025-06-30 | Gerri | NEW - SKU in SB shows as "Unknown Part" but SKU exists in DAX. Could this be a bug? 6 Impacts serials: HKYHBK005B100009YK UBIOSAMGS23P5H228337 UBIOSAMGS23P4U226257 G9QHCGP26WJ00004Y9 HKYHAY008R400009YH GH341350TLF1PHTA7 | bug |  |  | Raghu |  |  |  | In Progress | Gerri researched - will send file to Philip and Kelly to update part SKUs 7/28: Raghu to meet with Devs on this issue. 8/18: dev is working and will have resolution soon 9/8 - Maria to send recent examples and confirm if issues are present. ETA 9/16
35 | 2025-07-09 | Gerri | Verbiage/color change Error message when clicking Decrement Error message to be RED and states " Quantity scanned reduced by 1. Ensure quantity scanned is accurate before completing cycle count" | enhancements | [6 empty] | Open
36 | 2025-07-09 | Gerri | Verbiage/color change Error message when clicking Clear Error message to be RED and states " Quantity scanned was set to 0. Ensure quanity scanned is accurate before completing cycle count." | enhancements | [6 empty] | Open
37 | 2025-07-09 | Gerri | After clicking final report, message appears "Submitting final count… The final report will be emailed to the email addresses on file." The final report will be emailed to the inventory manager." Please remove duplicate sentence Confirm who will get email. Is this based on the SB configuration setup? Will final report be emailed to FIST mailbox?Asurion-SURAuditTeam@asurion.com | enhancements - 1 bug - 2 |  |  | Raghu |  |  |  | In Progress | Raghu will work on this in QA; to provide update next week 7/28: in QA, need to retest Duplicate sentence still appears. Final report wasn't sent to distro email. 7/30 8/18: duplicate sentence removed. Need demo in QA -- Raghu. Gerri sent distro email
38 | 2025-07-09 | Gerri | Why is SB marking scanned serials as "Invalid Serial Number in Part Serial # Search history? Is it because these are unrecognized parts that aren't in inventory? Impacted statuses and serial examples: DOA - TCPAUTOAPL1003038837 Discrepancy - TCPAUTOAPL1003231297 Installed - TCPAUTOAPL1003085842 LOST - TCPAUTOSAM6918035568 Lost_Audit - TCPAUTOAPL1003802754 Lost_Closed_Location - TCPAUTOAPL1003876714 Lost_Cycle_Count - TCPAUTOAPL1003529871 Lost_In_Transit_From_TLC - TCPAUTOAPL1003606009 Lost_In_Transit_To_TLC - TCPAUTOAPL1003683963 Lost_Theft - TCPAUTOAPL1003714577 Removed - TCPAUTOAPL1003434476 Return - TCPAUTOAPL1003251066 Padma to test in candyland. Review audit status. Confirm Logic | bug |  |  | Raghu |  |  |  | Resolved | Padma to verify in legacy 8/11: Gerri to validate 8/15 - : No “Invalid Serial Number” in the history after retest. Other issues found and will be listed at the bottom.
39 | 2025-07-09 | Gerri | Error made in Matrix for item#4 Need to update Action to: "Return" Change verbiage to: "The serial scanned will be returned at the end of this cycle count." | bug CR is created on 7/15 | 2025-07-31 |  | Raghu |  |  |  | In Progress | SBXA-16115 Fix by 7/25/25 8/11: Gerri to validate 8/15 Results: Update discrepancy status from “Matched” to “Unrecognized”. • Only instock/reserved serials should be Matched. 9/9: Testing still ongoing; in progress
40 | 2025-07-10 | Gerri | When scanning "LOST" serials, error message pops up "Error occurred inserting audit for serial or sku: TCPAUTOSAM6918035568. Please try again" Status change didn't occur in SB No action or updated status in final count file. See Matrix item#44 | bug | 2025-07-29 |  | Raghu | test1 |  |  | Resolved | Padma -- not receiving error Gerri - retest to confirm 7/31: No error message when scanning Verbiage still needs to be changed. Showing "The serial scanned will be returned at the end of this cycle count." The inventory increment at counting location but no updated status showing in final count. Action shows return. Need to update to Leave on rack. Will retest 8/4 with new data.Gerri
41 | 2025-07-10 | Gerri | Verbiage change needed Change to: "Serial scanned, will update to in stock at counting location." Lost_Audit Lost_Closed_Location Lost_Cycle_Count Lost_In_Transit_From_TLC Lost_In_Transit_To_TLC Lost_Theft Lost_Other 8/11 - Tied to item #38 | bug created CR on 7/15 |  |  | Raghu |  |  |  | Resolved | SBXA-16116 7/28: code in QA, need to retest 7/30: Gerri tested. logic didn't update. Same issues 8/11:Gerri to retest 8/15 - fixed
42 | 2025-07-10 | Gerri | All unexpected serials are populating as "Unrecognized" under Discrepancy status. Review final count file from 7/8. Gerri 7/14 - Status Mismatch/Part used aren't showing in UI. No concern with "Unrecognized" as discrepancy status. Impact: Reduce # of test cases from matrix. | bug |  |  | Raghu |  |  |  | Resolved
43 | 2025-07-14 | Gerri | Review Matrix item #5 - Wrong location / instock 2 out of 3 test serials didn't increment into counted location and final count not showing INC or action 004346840506445089 007270822709573202 7/14 - Raghu to confimr if inventory incremented/cremented correctly. Updating location A to RETURN Testing serial - SBAUTOMATION0000524323 |  | 2025-07-29 |  | Raghu |  |  |  | Resolved | Gerri will retry scenario. Will report results 7/30: Confirmed serial moved to instock in counting location. Final report show all correct actions. Added confirmation images to teams chat.
44 | 2025-07-14 | Gerri | Recording 2 - 40:57 21 serials missing from final count but appear in preview report screen. Was able to add notes to these line items. Notes visible in Part Serial Number Search (History) - 057056569901639800 Need all serials scanned to appear in final count. Mirror Legacy 7/14 - Sent attachment in Teams 7/15 - Padma to review - discuseed potential issue with part showing instock in multiple locations. | Bug | 2025-07-29 |  | Padma / Geri |  |  |  | Resolved | Picture Scenarios will be retested - 7/24 8/4: Gerri to flip serials today and retest
45 | 2025-07-14 | Gerri | Review Matrix item #6 - Wrong location / installed 1- Missing from final count file. 2 - 2 out of 5 show correct action/verbiage 3 - 3 show different verbiage and incorrect action. Why are they different if they're the same discrepancy/status? 057056569901639800 - RETURN 059619392607807574- RETURN 136348962102102146- RETURN 25425252561829 - Correct Action 25425262561830- Correct Action Note: Issue to be resolved in item51 | bug | [6 empty] | Resolved
46 | 2025-07-14 | Gerri | Serialized parts tab to be in Chronological order based on "Part Number" Legacy has all skus grouped Could we add a sorting button? What are our options? | bug |  |  | Raghu |  |  |  | Resolved | Raghu will check; there is no "sortable" button today. 8/11: change in QA
47 | 2025-07-14 | Gerri | Review Matrix item #7 - Wrong location / DOA 1 - Incorrect action during testing 2 - Missing from final count file 3 - Need to retest once fixed 086354087300477529 218228744605718134 TCPAUTOAPL1003158157 TCPAUTOAPL1037790543 NEW test serial : TCPAUTOAPL2019112635 | bug |  |  | Padma |  |  |  | In Progress | SBXA-16117 8/11: need to retest in QA 8/15: Results: Final report results differ from preview report. Preview report results should be the correct record. 8/18: Padma still under review/work
48 | 2025-07-14 | Gerri | Review Matrix item #8 - Wrong location / RETURN TCPAUTOAPL3131076378 CR to be created | bug |  |  | Padma |  |  |  | In Progress | 7/28: CR created sbxa-16115 8/11: Gerri to retest 8/15 Results: Investigate why the final report shows AT&T store as location name but inventory was in RETURN status for location JANUARY2024OSR 9/9: Still in progress. Research is still needed to determine root cause SBXA-16319
49 | 2025-07-14 | Gerri | Review Matrix item #8.5 - Wrong location /DISCREPANCY 1 - Missing from final count file. 2- Need to retest once fixed NEW test serial - SBAUTOMATION0000524324 | [7 empty] | Resolved | SBXA-16117 8/11: Gerri to retest 8/15: Fixed
50 | 2025-07-14 | Gerri | 1 - Pending Receiving serial marked as return with sku as unknown in final count. 2 - Part serial number search shows "partInventory.UNRECOGNIZED" in history. 3 - Why is SKU empty on report? 4- Verbiage " The serial or part scanned is not recognized. Please return at the end of the cycle count." 7058291400283910 Not in inventory table or associated to anything - Padma Answer:Used serial that didn't exist in SB. No action required. |  |  |  | Gerri |  |  |  | Resolved
51 | 2025-07-14 | Gerri | Review Matrix item #9 - Wrong location /Pending Receiving 1 - Confirm if SB will update the other locations pending receiving to RETURN or will FIS team need to manually update serials? Answer: SB to update location A's PR to RETURN. Update location B to instock/reserved - confirmed updated status at counting location This will cover all scenarios where location A needs update to RETURN 2 - Need SB view of serial status in Part Serial Number Search - only have store view. FIS team has visibility to view status from all locations. 010716914206579497 01198769631810 029166396001455686 010716914206579497 | bug created CR on 7/15 |  |  | Padma |  |  |  | Resolved | SBXA-16117 7/28: In QA ans ready to retest 7/30: Confirmed serial moved to instock in counting location. Final report shows all correct actions. See images in teams chat
52 | 2025-07-14 | Gerri | Review Matrix item #27 - Wrong location /LOST 1 - Missing from final count file. 2 - Update Action to: "Leave on Rack" 3 - Error message when scanning serial "Error occurred inserting audit for serial or sku: 161634124801283700. Please try again." 4- Confirm if inventory will increment properly 161634124801283700 SBAUTOMATION0000524415 7/15 -Padma was able to see error message. Will research and provide update. Create CR |  |  |  | Padma |  |  |  | Resolved | SBXA - 16117 8/11: Gerri to retest 8/15: Fixed
53 | 2025-07-15 | Gerri | Review Matrix item #26 - Not Counted / Reserved Final count file not showing "DEC" but SB is decrementing and updating serial status. Is this because the serial is reserved instead of instock? Answer: In stock qty column won't update to DEC due to part showing as RESERVED. How will we confirm the inventory is decremented in the report? |  |  | 2025-07-15 |  |  |  |  | Resolved
54 | 2025-07-16 | Gerri | Change discrepany title for Pending Receiving lines to" "Not Received" instead of "Unrecognized" | bug | [6 empty] | In Progress | 9/9- Need to test JIT scenario. Other scenarios work! :) 8/22 Anand working on updating
55 | 2025-07-16 | Gerri | Understanding the initial summary data vs post count preview report data 1 - What are the action required items? 2 - overages don't align 3 - Possible issue with over/not counted totals? Add pictures/data in new tab with item#55 | Bug? SBXA-16149 | [6 empty] | In Progress | SBXA-16149 8/11: Need to discuss further.
56 | 2025-07-21 | Padma | All serials that are set for returning are not shown in returns packing list | bug SBXA-16148 | [6 empty] | Resolved | SBXA-16148 8/18: Padma: issue is now resolved
57 | 2025-07-31 | Gerri | Final report doesn't show SKU for unknown/mis scanned parts. Preview screen in UI shows part number as "UNKNOWN" Need final report to mirror legacy Added Legacy file in teams chat | Bugs |  |  | Gerri |  |  |  | Resolved | 8/18: Resolved per Padma; Gerri to review 8/22: Gerri confirmed unknown is showing in UI,preview and final report
58 | 2025-08-04 | Gerri | Cycle count discrepancy returns in UI differs from data in RMA portal. only 2 serials captured in UI (packing list) 4 showing in RMA portal packing list See teams chat for examples and files | Bugs |  |  | Raghu |  |  |  | Resolved | 8/18: resolved
59 | 2025-08-05 | Gerri | Review Matrix item#6. wrong location/ insalled & DOA Scanned 2 installed/ 2 DOA parts, SB flipped serials to return after submitting final count. Preview report showed correct status and action. Final count shows part flipped to RETURN and updated in PSN. Confirm why preview report and final report have different outcomes? Adding preview report and final count in Teams chat | Bug | [6 empty] | In Progress | 8/15: Issue presnt during testing 9/9: SB team reviewing
60 | 2025-08-06 | Gerri | Additional lines with characters in final count report Possibly junk data Confirm if it will appear in production ( testing) | Bug | [6 empty] | Resolved | 8/18: will check testing in production. Gerri to send example to Raghu 8/22 - No additional lines found during final/preview report. Confirm if Raghu fixed
61 | 2025-08-07 | Gerri | Scan serial from RMA Pullback. RMA3743 Gerri created RMA 8.7.25 to get test serial -SBAUTOMATION0000524323 Confirm discrepancy status in final report Does it match PROD "Expected Return" ? Confirm discrepancy scenario for "Pending Return" |  |  |  | Gerri |  |  |  | In Progress | 8/18: Not able to reproduce result. Additional meeting on how to recreate error. COmpare legacy to AWS.
62 | 2025-08-07 | Padma | Clicking on Print is throwing shipping label not generated message but email is triggered with shipping label link. Need to understand why we're getting an error and unable to print from UI. 8/8 - Gerri confirmed 2 error messages populated. Issue is new and wasn't seen in previous testing | Bug |  |  | Padma |  |  |  | Resolved | 8/15: No issue found in latest test. 8/18: Issues with printe button in UI. Padma is working on this . SBXA-16319 8/22: No issue found in latest test. Gerri
63 | 2025-08-13 | Gerri | During testing found the discrepancy status differed from Matrix. Confirm if discrepancy status as “lost” is ok or if we need to update to “Unrecognized” Gerri to review with team. |  |  |  | Gerri/Anand |  |  |  | Resolved | 8/15: TCP team confirmed we can leave discrepancy status as LOST.
64 | 2025-08-13 | Gerri | Confirm why serial is moving to LOST and adding a line in PSN history. See example of happy below. Happy Path TCPAUTOAPAIPH1367925 Non-happy path - TCPAUTOAPL1003683963 Rule: Part Match Change rule in PSN history to : Lost part scanned Include JIT scenarios |  |  |  | Padma/Anand |  |  |  | In Progress | 8/18: Still under research. 8/22: Need list of rules for PSN history for FIST rsearching. Anand to change rule in PSN history to : Lost part scanned No impact to serial status/count
65 | 2025-08-13 | Gerri | Added QTY expected/return to Matrix. |  |  |  | Padma/Anand |  |  |  | Resolved | SBXA-16319 8/22 Expected QTY disappeared for all scenarios in final report. SB investigating. May be due to other on-going system updates. 9/9: team confirmed issue resolved.

## Updated Matrix 4.1.25
NEW AWS Cycle Count Truth Table
SERIALZED PARTS |  | No change to Discrepancy | [7 empty] | Impact on Inventory count THIS location |  | Impact on Inventory count OTHER location
Scenario | Discrepancy (Legacy) | Discrepancy (Next Gen) | Current Status | Testing Serial | Serial number | ServiceBench Action(s) | Scm Action (Next Gen) Investigate,Leave on Rack, Return | Servicer Action (in report) | Updated Status | In Stock | Available | In Stock | Available | Qty Expected | QTY Counted | TCP Category | Notes | Update Date | Agree on Logic (Y/N) Questions | Need Datazap for testing and verbiage | Pictures | Verbiage
1 | Not Counted | Not Counted | In Stock | 81944124442248 96343015768886 TCPAUTOAPA4146243996 TCPAUTOAPAIPH1395002 | TCP3SPTOSDONTUSE333104 TCP3SPTOSDONTUSE333131 TCP3SPTOSDONTUSE333143 TCP3SPTOSDONTUSE333145 TCP3SPTOSDONTUSE333147 | 1. Change status to "Discrepancy" | Investigate | Investigate | Discrepancy | Decrement | Decrement |  |  | 1 | 0 | Lost |  | 2025-10-09 | Fixed 9/9: New issue - some serials are not showing "DEC" in final report team will investigate . It may not impact at system level. 9/9: QTY expected issue - RESOLVED | N |  | NA
2 | Status Mismatch | Unrecognized | Installed | TCPAUTOAPL1003085842 TCPAUTOAPL1003038837 | SEAOSAMGS23O2E126296 | – | Return through DOA/Core process | Return Part | no change |  |  |  |  | 0 | 1 | Overage |  | 2025-09-09 | 9/9 - resolved 1. change discrepancy status to "Unrecognized" 2. change qty expected/counted | N | #VALUE! | The serial scanned will be returned at the end of this cycle count.
3 | Status Mismatch | Unrecognized | DOA | TCPAUTOAPL1003831839 | TCPSRFSPRAPL121212143 TCPSRFSPRAPL121212134 TCPSRFSPRAPL121212130 TCPSRFSPRAPL121212126 | – | Return through DOA/Core process | Return Part | no change |  |  |  |  | 0 | 1 | Overage |  | 2025-09-09 | 9/9 - resolved 1. change discrepancy status to "Unrecognized" 2. change qty expected/counted | N | #VALUE! | The serial scanned will be returned at the end of this cycle count.
4 | Status Mismatch | Unrecognized | Return | TCPAUTOAPL1003251066 TCPAUTOAPL1003256473 TCPAUTOAPL1003265902 TCPAUTOAPL1003275293 | TCPAUTOAPL1093373335 TCPAUTOAPL1093373346 | – | Return | Return Part | ES_Return |  |  |  |  | 0 | 1 | Overage |  | 2025-10-09 | Fixed 1. change discrepancy status to "Unrecognized" showing matched in testing 8/13 2. change qty expected/counted 9/9 - Confirmed with Padma that any unrecognized serial will move from RETURN to ES_RETURN = Expected Return | N |  | The serial scanned will be returned at the end of this cycle count.
4.5 | Status Mismatch | Unrecognized | Discrepancy | TCPAUTOAPL1003142938 TCPAUTOAPL1003231297 03948316235501 63993654851446 98645383038490 | TCPSRFSPRAPL121212132 TCPSRFSPRAPL121212133 | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Overage |  | 2025-08-18 | Y | N | #VALUE! | Serial scanned, will update to in stock at counting location.
5 | Incorrect location | Wrong location | In Stock | 002664638402450720 004346840506445089 007270822709573202 New Test Serial - SBAUTOMATION0000524323 | TCPSRFSPRAPL121212138 | 1. Transfer part to this location | Leave on Rack | – | In Stock | Increment | Increment | Decrement | Decrement | 0 | 1 | Location Variance | 1 - Error message appears for some serials. See image 2 - 7/14 - Raghu to confimr if inventory incremented/cremented correctly. 3 - Only 002664638402450720 shows happy path 4 - marking location A to RETURN Possibly JIT serial when tested, Restest needed | 2025-09-09 | 9/9: QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
6 | Incorrect location | Wrong location | Installed | 8/5/25 SBAUTOMATION0000524321 TCPAPL10763948878 - RETURN | 75412589 | – | Return through DOA/Core process | Return Part | Installed |  |  |  |  | 0 | 1 | Location Variance | 8/5/25 - Gerri scanned 2 installed parts, SB flipped serial to return after submitting final count. Preview report showed correct status and action. Final count shows part flipped to RETURN and updated in PSN. Need to fix Field to return parts through RM return in RMA Portal | 10/13/2025 | Fixed 10/13/25 9/9 same issue Waiting on SB team to identify root cause. Issue: Preview/final report show different results Preview report correct serial status updates to RETURN - don't need serials to flip incorrect action in final report - Should be return through DOA/Core Process | N Issue log issue #6 | #VALUE! | Happy Path = Serial scanned shows at a different location in the system. Please return at the end of the cycle count.
7 | Incorrect location | Wrong location | DOA | TCPAUTOAPL1037790543 NEW test serial - TCPAUTOAPL2019112635 |  | – | Return through DOA/Core process | Return Part | DOA |  |  |  |  | 0 | 1 | Location Variance | Field to return parts through RM return in RMA Portal | 10/13/2025 | Fixed 10/13/25 Updated 9/9 same issue Waiting on SB team to identify root cause. Issue: Preview/final report show different results Preview report correct 1.Final report serial status: RETURN 2.Final report Action: RETURN | N Waiting on SB team to fiz logic 9/9 Issue log issue #7 | #VALUE! | Serial scanned shows at a different location in the system. Please return at the end of the cycle count.
8 | Incorrect location | Wrong location | Return | 119703662508794992 SBAUTOMATION0000524414 TCPAUTOAPL3131076378 TCPAUTOAPL3131076379 139411895304794689 | DKH9466B9GWH1NRA7 | – | Return | Return Part | Expected Return ES_RETURN |  |  |  |  | 0 | 1 | Location Variance | 10/13/25 Due to logic, serial will update to ES_RETURN after scanning into count | 10/13/2025 | FIXED - Inventory updated in PSN to counting location 10/9 9/9: Issue PSN current history location name isn't updating to counting location. 8/15 Results: Investigate why the final report shows AT&T store as location name but inventory was in RETURN status for location JANUARY2024OSR | N Issue log issue #48 | #VALUE! | The serial scanned will be returned at the end of this cycle count.
8.5 | Incorrect location | Wrong location | Discrepancy | SBAUTOMATION0000524326 | TCPSRFSPRAPL121212139 | 1. Transfer part to this location 2. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Location Variance |  | 2025-09-09 | Y | N | #VALUE! | Serial scanned is located at a different location in the system. Making necessary adjustments.
9 | Incorrect location | Wrong location | Pending Receiving | 7058291400283910 - Item#49 010716914206579497 01198769631810 029166396001455686 | SEAOSAM6946M2Q000269 | 1. Receive Part at this location | Leave on Rack | – | In Stock Showing "Reserved" | Increment | Increment |  |  | 0 | 1 | Location Variance | 1 - 7058291400283910 - Incorrect action, , verbiage,discrepancy status,Sku empty 2 - 010716914206579497 01198769631810 029166396001455686 Answer:Update location B to instock/reserved - confirmed updated status at counting location 3 - Need SB view of serial status in Part Serial Number Search - only have store view. FIS team has visibility to view status from all locations. | 2025-09-09 | ? What is the impact for other location's pending receiving? How will their inventory be fixed or will it remain PR until manually updated? Recent change to not add 2nd line only update the location line | N | Picture | Pending receiving serial will be received at this location upon cycle count completion.
10 | Not Received | Not Received | Pending Receiving | 8/22 Post Call TCPAUTOAPAIPH1234801 | UBIOSAMGS24O9R180290 | 1. Receive Part | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Overage |  | 2025-09-09 | 9/9 Change discrepancy status to Not Received - resolved 2. QTY expected issue | N |  | Pending Receiving serial will be received at this location upon cycle count completion.
11 | Unrecognized | Unrecognized | any |  |  | – | Return | Return Part | no change |  |  |  |  | 0 | 1 | Exclude | serial number pattern match - unknowns (mis scans) or Greater than 10 characters | 10/9/2025 | Fixed Issue log#57 8/22 1.Confirmed part number in final report show as "UNKNOWN " 2. QTY expected issue | N |  | The serial or part scanned is not recognized. Please return at the end of the cycle count.
12 | Unrecognized | Unrecognized | N/A |  |  | – | Investigate | Return Part | no change |  |  |  |  | 0 | 1 | Exclude | no pattern match - unknowns (mis scans) Less than 10 characters | 10/9/2025 | Fixed Issue log#57 8/22 1.Confirmed part number in final report show as "UNKNOWN " 2. QTY expected issue | N |  | No quantity counted, please investigate and ensure part was not missed during count Unknown
15 | Status Mismatch | Unrecognized | Expected Return | Need to get serial example for tes | SEAOSAMGS23P2S215554 | – | Return | Return Part | ES_RETURN |  |  |  |  | 0 | 1 | Overage | When scanning serial SBAUTOMATION0000524323 from completed RMA Pullback RMA3743, SB verbiage says inventory is from different location. Preview/Final report shows incorrect discrepancy status. | 10/13/2025 | FIXED 10/13/25 Need to test 10/9 8:22: Anand to research Legacy logic to resproduce 8/18: Not able to reproduce result. Additional meeting on how to recreate error. Compare legacy to AWS. | N |  | The serial scanned will be returned at the end of this cycle count.
16 | Status Mismatch | Unrecognized | Removed | TCPAUTOAPL1003382436 TCPAUTOAPL1003434476 TCPAUTOAPL1003450362 TCPAUTOAPL1003454582 | FVFZDAASLYWH | – | Leave on Rack | – | no change |  |  |  |  | 0 | 1 | Exclude | Action/Verbiage need to be updated for testing Removed status used for MacBooks and Mifis. IT Asset team now manages this inventory. We don't want field to return these assets as they're no longer in inventory. | 2025-09-09 | resolved 1. Change action to : Leave on Rack 2. Change verbiage : "Serial scanned, no updates required." | N |  | "Serial scanned, no updates required.
17 | Matched | Matched | Reserved |  | SEAOSAMGS22O9T180819 | – | Leave on Rack | – | no change |  |  |  |  | 1 | 1 | No Action |  | 10/14/2025 | Fixed 10/14 Need to test in QA Ask Padma for testing serial | N |  | Serial scanned, no updates required.
18 | Matched | Matched | In Stock | 80616339367294 81944124442248 96343015768886 TCPAUTOAPA4146021896 |  | – | Leave on Rack | – | no change |  |  |  |  | 1 | 1 | No Action |  | 2025-09-09 | Y | N |  | Serial scanned, no updates required.
19 | PART_USED | Unrecognized | Lost_Cycle_Count | TCPAUTOAPL1003529871 TCPAUTOAPL1003542024 TCPAUTOAPL1003558052 TCPAUTOAPL1003603263 | SEAOSAMGS23O5L147606 | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
20 | Part used | Unrecognized | LOST_IN_TRANSIT_FROM_TLC | TCPAUTOAPL1003606009 TCPAUTOAPL1003607882 TCPAUTOAPL1003662211 TCPAUTOAPL1003672646 | G9P4394QMCQ1PHRAB | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
21 | Part used | Unrecognized | LOST_IN_TRANSIT_TO_TLC | TCPAUTOAPL1003683963 TCPAUTOAPL1003688748 TCPAUTOAPL1003705707 TCPAUTOAPL1003706664 |  | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
22 | Part used | Unrecognized | LOST_THEFT | TCPAUTOAPL1003714577 TCPAUTOAPL1003748229 TCPAUTOAPL1003799814 TCPAUTOAPL1003802189 | SEAOSAMGS20O8D168913 | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
23 | Part used | Unrecognized | LOST_AUDIT | TCPAUTOAPL1003802754 TCPAUTOAPL1003805622 TCPAUTOAPL1003816545 TCPAUTOAPL1003835915 |  | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
24 | Part used | Unrecognized | LOST_OTHER | TCPAUTOAPL1003849662 TCPAUTOAPL1003849933 TCPAUTOAPL1003853252 TCPAUTOAPL1003861971 | SEAOSAMGS20O8D168913 | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
25 | Part used | Unrecognized | LOST_CLOSED_LOCATION | TCPAUTOAPL1003876714 TCPAUTOAPL1003899196 TCPAUTOAPL1003948747 TCPAUTOAPL1003956379 |  | 1. Change status to "In Stock" | Leave on Rack | – | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | These are Finance terminal statuses after inventory is written out of DAX. | 2025-09-09 | 9/9: Moving the discrepancy status from LOST back to Unrecognized due to system causing issue. Won't allow serials to flip to instock. Best solution | N |  | Serial scanned, will update to in stock at counting location."
26 | Not Counted | Not Counted | Reserved | TCPAUTOSAM6918412445 TCPAUTOSAM6918392435 TCPAUTOSAM6918351803 | UBIOSAMGS23P2M214756 | 1. Change status to "Discrepancy" | Investigate | Investigate | Discrepancy |  |  |  |  | 1 | 0 | Lost | Final count file not showing "DEC" but SB is decrementing and updating serial status. File: FINAL_CycleCountReport_SB78839372_AT&T Store_AT&T STORE_07112025-1153 with FIST notes | 10/14/25 | Fixed 10/14/25 Need to test in QA Ask Padma for JIT testing serial | N | #VALUE! | No verbiage
27 | Incorrect location | Wrong location | LOST | '118203303305850391 | SEAOSPRAER1M3U000004 | 1. Change status to "In Stock" | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | Fixed | 2025-09-09 | SB will transfer inventory from one location to another . PSN will only show 1 line in current history | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments
28 | Incorrect location | Wrong location | Expected Return | Need to get serial example for test 7/10. Do I need to create RMA pullback for SB to know it's an expected return serial? | TLCPSAMSUNGM3B000122 |  | Return | – | No change ES_RETURN |  |  |  |  | 0 | 1 | Location Variance |  | 10/14/25 | FIXED 10/14/25 9/9: Anand to research Legacy logic to resproduce 8/18: Not able to reproduce result. Additional meeting on how to recreate error. Compare legacy to AWS. | N |  | Serial scanned shows at a different location in the system. Please return at the end of the cycle count.
32 | Not Received | Not Received | Pending Receiving | TCPAUTOSAM6918351803 TCPAUTOSAM6918392435 TCPAUTOSAM6918412445 TCPAUTOSAM6918456848 TCPAUTOSAM6918470659 | G9Q4365U28W21KHAJ |  | Leave on Rack | Increment | Reserved |  |  |  |  | 0 | 1 | Overage | JIT parts are set to reserved | 2025-09-09 | 9/9 1.Change Discrepancy status to " Not Received" | N | #VALUE! | Pending receiving serial will be received at this location upon cycle count completion.
44 | Status Mismatch | Unrecognized | Lost | TCPAUTOSAM6918035568 TCPAUTOSAM6918337232 TCPAUTOSAM6918613232 TCPAUTOSAM6918693277 | SEAOSAM6961KCE000690 | 1. Change status to "In Stock" | Leave on Rack | Increment | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | Fixed | 2025-09-09 | Y | N |  | Serial scanned, will update to in stock at counting location."
47 | Status Mismatch | Unrecognized | Pending Return | Need to get serial example for test 7/10 SEAOSAMNT20O8T173132 production serial example | SEAOSAMNT20O8T173132 |  | Return |  | no change |  |  |  |  | 0 | 1 | Overage |  | 2025-09-09 | 9/9 - resolved 8:22: Anand to research Legacy logic to resproduce 8/18: Not able to reproduce result. Additional meeting on how to recreate error. Compare legacy to AWS. | N |  | The serial scanned will be returned at the end of this cycle count.
48 | Incorrect location | Wrong location | Pending Return | Need to get serial example for tes | SEAOSAM6975K5C000751 |  | Return |  | no change |  |  |  |  | 0 | 1 | Location Variance | Serial was shipped to store in DAX Part wasn't used or tied to RMA Part serial number search shows Status: Part Used Invalid SP Reach out to Raghu if another scneario appears - | 2025-09-09 | 9/9 - resolved 8:22: Anand to research Legacy logic to resproduce 8/18: Not able to reproduce result. Additional meeting on how to recreate error. Compare legacy to AWS. | N | #VALUE! | Serial scanned shows at different location in the system. Please return at the end of the cycle count.
50 |  | Wrong Location | Lost - Cycle Count |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
51 |  | Wrong Location | LOST_IN_TRANSIT_FROM_TLC |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
52 |  | Wrong Location | LOST_IN_TRANSIT_TO_TLC |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
53 |  | Wrong Location | LOST_THEFT |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
54 |  | Wrong Location | LOST_AUDIT |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
55 |  | Wrong Location | LOST_OTHER |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
56 |  | Wrong Location | LOST_CLOSED_LOCATION |  |  | 1. Transfer part to this location | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | 7/29/2025 - Added new scenario to cover wrong location scenarios for documentation | 2025-09-09 | 8/22 QTY expected issue - resolved | N |  | Serial scanned is located at a different location in the system. Making necessary adjustments.
58 | Status Mismatch | Unrecognized | Lost |  | SEAOSAM6961KCE000690 |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | Anand asked that Gerri add scenario for JIT serial Gerri to retest when team says it's ready. | 2025-09-09 | 9/9 - resolved Need to test in QA Wairing on SB team to fix logic | N |  | Serial scanned, will update to instock at counting location.
59 | Incorrect location | Wrong location | Return |  | DKH9466B9GWH1NRA7 | – | Return | Return Part | Expected Return ES_RETURN |  |  |  |  | 0 | 1 | Location Variance | JIT serial | 10/14/25 | Fixed 10/14/25 Ready to test10/9 1. Change verbiage 2. No change to status. Logic is updating to reserved. Need to update logic | N | #VALUE! | The serial scanned will be returned at the end of the cycle count
60 | Incorrect location | Wrong location | LOST | 161634124801283700 SBAUTOMATION0000524415 | SEAOSPRAER1M3U000004 | 1. Change status to "In Stock" | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT serial | 2025-09-09 | 9/9 resolved 8/15: Why isn't reserved inventory incrementing? It is because the column only counts In Stock parts? | N |  | Serial scanned, will update to reserved at counting location.
61 |  | Not Received | Pending Receiving | TCPAUTOSAM6918521209 |  |  | Leave on Rack |  | Reseved |  |  |  |  | 0 | 1 | Overage | JIT parts are set to reserved | 2025-10-09 | Fixed 10/9 8/22 1. QTY Expected issue 2.Change discrepancy status to "Not Received" | N |  | Pending receiving serial will be received at this location upon cycle count completion.
62 |  | Unrecognized | LOST |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT parts are set to reserved | 2025-09-09 | 9/9 resolved Need to test in QA Wairing on SB team to fix logic | N |  | Serial scanned, will update to in stock at counting location.
63 | Incorrect location | Wrong location | Discrepancy |  | 1. Transfer part to this location 2. Change status to "In Stock" |  | Leave on Rack |  | INSTOCK | Increment | Increment |  |  | 0 | 1 | Location Variance | JIT parts are set to reserved | 2025-10-14 | Fixed 10/14/25 10/9 Ready to test 9/9 : Invnetory ID issue. Padma needs to test in QA Wairing on SB team to fix logic | N |  | Serial scanned, will update to in stock at counting location.
64 |  | Unrecognized | Lost - Cycle Count |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
65 |  | Unrecognized | LOST_IN_TRANSIT_FROM_TLC |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
66 |  | Unrecognized | LOST_IN_TRANSIT_TO_TLC |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
67 |  | Unrecognized | LOST_THEFT |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
68 |  | Unrecognized | LOST_AUDIT |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
69 |  | Unrecognized | LOST_OTHER |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
70 |  | Unrecognized | LOST_CLOSED_LOCATION |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-09-09 | 8/22: Added scenario to cover JIT scenarios - resolved | N |  | Serial scanned, will update to in stock at counting location."
71 |  | Wrong Location | Lost - Cycle Count |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
72 |  | Wrong Location | LOST_IN_TRANSIT_FROM_TLC |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
73 |  | Wrong Location | LOST_IN_TRANSIT_TO_TLC |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
74 |  | Wrong Location | LOST_THEFT |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
75 |  | Wrong Location | LOST_AUDIT |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
76 |  | Wrong Location | LOST_OTHER |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
77 |  | Wrong Location | LOST_CLOSED_LOCATION |  |  |  | Leave on Rack |  | In Stock | Increment | Increment |  |  | 0 | 1 | Gain | JIT | 2025-10-13 | 10/13 FIXED 10/9: SB team need to test to confirm | N
78 |  | Wrong Location | Reserved |  |  |  | Leave on Rack |  | INSTOCK | Increment | Increment |  |  | 0 | 1 | Location Variance | JIT | 2025-10-14 | FIXED10/14/25 10/9: SB team need to test to confirm | N |  | Serial scanned will update to instock at counting location.
13 | Lost Part | ? | Lost |  |  | – | ? | Return Part | no change | [7 empty] | consumable repair part |  | Unable to reproduce in QA. Will resolve if seen in Production | See if appear in Production |  | Not needed for now - June620205
14 | Lost Part | ? | Lost |  |  | 1. Change status to "In Stock" | ? | – | In Stock | Increment | Increment | [5 empty] | scheduable asset |  | Unable to reproduce in QA. Will resolve if seen in Production | See if appear in Production
29 | INVALID_LOCATION | ? | Discrepancy |  | SAM-GS23U-1000-KIT | 1.Changes status to Return | Return |  | Return | [7 empty] | Sb shows part number as serial. Only 1 example for all locations | 2025-08-18 | Unable to reproduce in QA. Will resolve if seen in Production | See if appear in Production | #VALUE!
30 | INVALID_LOCATION | ? | Return |  | DKH9466B9GWH1NRA7 |  | Return |  | no change | [7 empty] | Send to Raghu - confirm if it's a bug. And will not impact AWS | 2025-08-18 | Unable to reproduce in QA. Will resolve if seen in Production | See if appear in Production
33 | PART_USED | Part used | DOA | TCPAUTOAPL1003062837 TCPAUTOAPL1003198448 TCPAUTOAPL1003212653 TCPAUTOAPL1003245199 | C119387ZCR8G191TD |  | Return through DOA/Core process | – | no change | [7 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | Removed as Unrecognized replaced Part used scenarios | N
34 | PART_USED | Part used | Installed | TCPAUTOAPL1003038837 TCPAUTOAPL1003049307 TCPAUTOAPL1003085842 TCPAUTOAPL1003093099 | SEAOSAMGS23O8A167967 |  | Return through DOA/Core process | – | no change | [7 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | Removed as Unrecognized replaced Part used scenarios | N
35 | PART_USED | Part used | Reserved | ? | SEAOSAMGS22P4U226289 |  | Leave on Rack | [9 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | Removed as Unrecognized replaced Part used scenarios | N
36 | PART_USED | Part used | Return | TCPAUTOAPL1003251066 TCPAUTOAPL1003256473 TCPAUTOAPL1003265902 TCPAUTOAPL1003275293 | C3F1113M2F8HLK7AE |  | Return | – | no change | [7 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | Removed as Unrecognized replaced Part used scenarios | N
37 | PART_USED | Part used | Discrepancy | TCPAUTOAPL1003142938 TCPAUTOAPL1003231297 TCPAUTOAPL1003242614 TCPAUTOAPL1003250856 03948316235501 63993654851446 98645383038490 | SEAOGS23P5GOBD193572 |  | Leave on Rack | Increment | IN_STOCK | Increment | Increment | [5 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | Removed as Unrecognized replaced Part used scenarios | N
39 | PART_USED | Part used | Lost | TCPAUTOSAM6918035568 TCPAUTOSAM6918337232 TCPAUTOSAM6918613232 TCPAUTOSAM6918693277 | F8Y413400MT231LBL |  | Leave on Rack | Increment | IN_STOCK | Increment | Increment | [5 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | Removed as Unrecognized replaced Part used scenarios | N
40 | Return | ? | <Status> |  | SUR-ABT 2000 |  | Investigate? | [9 empty] | Possibly Remove if "Unrecognized" with cover non-happy path scenarios | 2025-08-18 | 7/14 - Haven't seen this issue in QA. May not impact AWS | N
41 | Return | ? | Return | Example from August 25 CC: DRCHC10014H0000AY3 | (9D):2343 HH9 OSAMGS20P2G213440 SUR-ABT 2000 SEAOGS24P5GOBM195239 J0MHBX003FV0000U64 J0MHC101FQY0000U64 |  | Return | [9 empty] | Send to RaghuDuplicate serials in current line in PSN | 2025-08-18 | Current status line shows 2 records for same location Impact: final CC shows 2 records with different statuses/actions 8/18: Find example to send to Raghu issue log#21 "This is data issue and bug in existing cycle count. " | Discuss | #VALUE!
45 | Status Mismatch | Mirror Sceanrio #18 Matched | In Stock |  | DRCHAZ0039U000023V |  | Leave on Rack | – | no change | [8 empty] | 2025-08-18 | Removed duplicate scenario#18 Change logic to ensure in stock parts show as Matched. Impact: Current logic is causing shrink. SB is asking field to return parts but not updating the serial to RETURN. Raghu looking into bug. On-going email chain | See if appear in Production
49 | Matched | Mirror Sceanrio #2 Status Mismatch | Installed |  | G9P4332PC7014YCA1 | – | Return through DOA/Core process | Return Part | Installed | [7 empty] | 7/14 - Haven't seen this issue in QA. May not impact AWS | 2025-08-18 | Removed duplicate scenario #2 Why is the discrepancy status Matched but the current status is installed? Should discrepancy be Part used or Status Mismatch | See if appear in Production |  | ?
NON-SERIALZED PARTS | [9 empty] | Impact on Inventory count THIS location |  | Impact on Inventory count OTHER location
Scenario | Discrepancy |  | Current Status |  |  | ServiceBench Action(s) |  | Servicer Action (in report) | Updated Status | In Stock | Available | In Stock | Available |  |  |  | Notes
| Quantity Under |  |  |  | IB-0727 | 1. Update quantity |  | – |  |  | –
2 | Quantity Over |  |  |  | MB-0727 | 1. Update quantity |  | – |  | – | –
3 | Not Received |  |  |  | IB-0727 | 1. Receive Part 2. Update Quantity |  | – |  | Increment | Increment
4 | Unrecognized |  |  |  |  | – |  | – |  | – | –
5 | Lost Part |  |  |  |  | 1. Change status to "In Stock" |  | – |  | Increment | Increment
| Date |  | Change in this version
v03 | 08.12.2018 |  | Added scenario 4.5 - to cover case of scan / Over for part in Discrepancy status at this location.
Added scenario 8.5 - to cover case of no match / Discrepancy at one location, followed by a scan / Over for same part at a dfferent location.
Added scenarios 13 and 14 - to cover case of parts in Lost status - both for consumable parts (13) and non-consumable "schedulable asset" parts (14)
v02 | 04.19.2018 |  | Clarified the 2 types of "unrecognized"
#11: serial number is known to SB, but at another SP, OR serial number is NOT known, but pattern matches Asurion serial number pattern.
#12: serial number is NOT known to SB, AND serial number does NOT match Asurion serial number pattern. ("UNKNOWN")
v03 | 02.09.2019 |  | Added rules for non-serialized parts

## Sheet3 (hidden)
#VALUE!

## Recording Links
# | Date | Title | Description | Link | Passcode | Owner
1 | 2025-05-07 | Quick Connect to discuss testing Cycle Count on AWS. | Intro Demo of Happy Path to Next Gen *Out of time to review Non-happy paths* | https://asurion.zoom.us/rec/share/y4xKy3xRCRKwpqwcHkIXlqkxw8UOlc4DQlSQ-SnHqVmETURV8wb05ciXIlD-Fimj.qNYtPma8If7VWJNJ | 7Vu$vfX@ | Kelly
2 | 2025-05-12 | Demo on SUR 3PL consolidation of count files | TCP Consolidation process when counts arrive in mailbox | https://asurion.zoom.us/rec/share/5m2_kn-WW2kIypqvH8S6lHdvjo3hw76fRv_XTyHuxPnE_D9xPNYxZsVO0Utacs-9.TgFEEr-i0exBGRYD?startTime=1746801361000 | G0HvY=gR | Maru
3 | 2025-05-12 | Moving Cycle Count to AWS | 1. Updates and key changes regarding the cycle count migration to AWS. 2. Remote technician training. 3. Possible impacts to Power Apps. 4. Rollout strategy. | https://asurion.zoom.us/rec/share/YNDlEAFZP9mwLqeNBzLxqZgM7tprdsnXqZBnQl2MK-RbkMYgo-6i7vs9DhOgjkzu.GZ-lENIcDyvdGbQd | p7z!x3v% | Kelly
4 | 2025-05-19 | Demo of SUR Cycle Count in AWS (ServiceBench) | Intro Demo with Cherly & Jamie for WI support. New feature shown for cycle count discrepancies (RMA portal would house CCD labels/packing list) | https://asurion.zoom.us/rec/share/owRTWTzh5ZXDlTfpdoUVnO_8AOcVu_8uTW1SgQpGM7a7w0EHvlMbv87LfWzZUUfk.F-4_w_Bpc8auavJd | 4q=yOm^S
5 | 2025-05-21 | Weekly Sync on Testing SUR Cycle Count | Discuss Open issue / questions | https://teams.microsoft.com/l/meetingrecap?driveId=b%21vG20c6O-UE2f7uhzj4zbDG8X_pZ_PP5EvCCl736P88x9g1QSj4DgQaRci7vDpcHH&driveItemId=01X73AQ4YM56TBUBAUUNCLNJK6KW5ON72W&sitePath=https%3A%2F%2Fasurion-my.sharepoint.com%2F%3Av%3A%2Fp%2Fkelly_shaw%2FEQzvphoEFKNEtqVeVbrm_1YB-VBVncCmeeQGiTOF8IHjlA&fileUrl=https%3A%2F%2Fasurion-my.sharepoint.com%2Fpersonal%2Fkelly_shaw_asurion_com%2FDocuments%2FRecordings%2FWeekly%2520Sync%2520on%2520Moving%2520SUR%2520Cycle%2520Count%2520to%2520AWS-20250521_163154-Meeting%2520Recording.mp4%3Fweb%3D1&iCalUid=040000008200E00074C5B7101A82E00807E90513440636E004C5DB01000000000000000010000000E59F28F14CDB7543BF4A48649DBAB094&masterICalUid=040000008200E00074C5B7101A82E00800000000440636E004C5DB01000000000000000010000000E59F28F14CDB7543BF4A48649DBAB094&threadId=19%3Ameeting_OGVhYjQxZTMtNjAzMS00MDUxLWE1ZGItZjRhZjg1ZjA5OWUw%40thread.v2&organizerId=108fb88e-b845-467d-92a5-4f7ad9b62674&tenantId=64e5ad32-cb04-44df-8896-bed5d7792429&callId=f4aea029-ab7c-44e6-8285-e77b9b6af539&threadType=Meeting&meetingType=Recurring&subType=RecapSharingLink_RecapCore |  | Kelly
6 | 2025-05-27 | Weekly Sync on Testing SUR Cycle Count | Discuss Open issue / questions | No Recording Available
7 | 2025-06-02 | Weekly Sync on Testing SUR Cycle Count | Discuss Open issue / questions | https://teams.microsoft.com/l/meetingrecap?driveId=b%21vG20c6O-UE2f7uhzj4zbDG8X_pZ_PP5EvCCl736P88x9g1QSj4DgQaRci7vDpcHH&driveItemId=01X73AQ44Q37T4BT2QIRGZ22G42QE3UFW2&sitePath=https%3A%2F%2Fasurion-my.sharepoint.com%2F%3Av%3A%2Fp%2Fkelly_shaw%2FEZDf58DPUERNnWjc1Am6FtoBcrcVAs7OK9WmcJLwvv6nag&fileUrl=https%3A%2F%2Fasurion-my.sharepoint.com%2Fpersonal%2Fkelly_shaw_asurion_com%2FDocuments%2FRecordings%2FWeekly%2520Sync%2520on%2520Moving%2520SUR%2520Cycle%2520Count%2520to%2520AWS-20250602_110318-Meeting%2520Recording.mp4%3Fweb%3D1&iCalUid=040000008200E00074C5B7101A82E00807E90602440636E004C5DB01000000000000000010000000E59F28F14CDB7543BF4A48649DBAB094&masterICalUid=040000008200E00074C5B7101A82E00800000000440636E004C5DB01000000000000000010000000E59F28F14CDB7543BF4A48649DBAB094&threadId=19%3Ameeting_OGVhYjQxZTMtNjAzMS00MDUxLWE1ZGItZjRhZjg1ZjA5OWUw%40thread.v2&organizerId=108fb88e-b845-467d-92a5-4f7ad9b62674&tenantId=64e5ad32-cb04-44df-8896-bed5d7792429&callId=622c3875-c0f3-4266-8d4c-cb6ee2df3dae&threadType=Meeting&meetingType=Recurring&subType=RecapSharingLink_RecapCore |  | Kelly
8 | 2025-06-11 | Weekly Sync on Testing SUR Cycle Count | Discuss Open issue / questions | No Recording Available
9 | 2025-06-16 | Weekly Sync on Testing SUR Cycle Count | Discuss Open issue / questions | https://teams.microsoft.com/l/meetingrecap?driveId=b%21vG20c6O-UE2f7uhzj4zbDG8X_pZ_PP5EvCCl736P88x9g1QSj4DgQaRci7vDpcHH&driveItemId=01X73AQ42LAXPD6HRAPZFIIBMXURQEYPQG&sitePath=https%3A%2F%2Fasurion-my.sharepoint.com%2F%3Av%3A%2Fp%2Fkelly_shaw%2FEUsF3j8eIH5KhAWXpGBMPgYBAa2_BT-_JryTTHEPfwSYig&fileUrl=https%3A%2F%2Fasurion-my.sharepoint.com%2Fpersonal%2Fkelly_shaw_asurion_com%2FDocuments%2FRecordings%2FWeekly%2520Sync%2520on%2520Moving%2520SUR%2520Cycle%2520Count%2520to%2520AWS-20250616_110317-Meeting%2520Recording.mp4%3Fweb%3D1&iCalUid=040000008200E00074C5B7101A82E00807E90610440636E004C5DB01000000000000000010000000E59F28F14CDB7543BF4A48649DBAB094&masterICalUid=040000008200E00074C5B7101A82E00800000000440636E004C5DB01000000000000000010000000E59F28F14CDB7543BF4A48649DBAB094&threadId=19%3Ameeting_OGVhYjQxZTMtNjAzMS00MDUxLWE1ZGItZjRhZjg1ZjA5OWUw%40thread.v2&organizerId=108fb88e-b845-467d-92a5-4f7ad9b62674&tenantId=64e5ad32-cb04-44df-8896-bed5d7792429&callId=535ed94f-a104-477f-ba20-589f43c8820e&threadType=Meeting&meetingType=Recurring&subType=RecapSharingLink_RecapCore |  | Kelly

## item55 (hidden)
Part number | Part Type | In stock | Reserved | Matched | Over | Part number | Part Type | In stock | Reserved | Matched | Over
APL1003-KIT | Serialized | 34 |  |  |  | APL1003-KIT | Serialized | 34 |  | 34
APA4145-BLK-KIT | Serialized | 23 |  |  |  | APA4145-BLK-KIT | Serialized | 23 |  | 23
APA4146-BLK-KIT | Serialized | 22 |  |  |  | APA4146-BLK-KIT | Serialized | 22 |  | 22
SAM12009-KIT | Serialized | 8 |  |  |  | SAM12009-KIT | Serialized | 8 |  | 8
APA-IPH14-BGR-BLK-KIT | Serialized | 6 |  |  |  | APA10004-KIT | Serialized |  |  |  | 13
SAM-ZFOLD45G-1004-KIT | Serialized | 6 |  |  |  | APA-IPH14-BGR-BLK-KIT | Serialized | 6 |  | 6
APA-IPH13PM-1000-KIT | Serialized | 2 |  |  |  | SAM-ZFOLD45G-1004-KIT | Serialized | 6 |  | 6
APA-IPH14-1000-KIT | Serialized | 1 |  |  |  | APL-313-1003-KIT | Serialized |  |  |  | 5
SUR-SAM-1052 | Non-Serialized | 4 |  |  |  | APA-IPH13PM-1000-KIT | Serialized | 2 |  | 2
[6 empty] | APL4122-KIT | Serialized |  |  |  | 2
[6 empty] | APA-IPH14-1000-KIT | Serialized | 1 |  | 1
[6 empty] | APA9153-GLD-KIT | Serialized |  |  |  | 2
[6 empty] | APA4143-BLK-KIT | Serialized |  |  |  | 2
[6 empty] | SAM6918-KIT | Serialized |  |  | 2
[6 empty] | APL1037-KIT | Serialized |  |  |  | 1
[6 empty] | APA-IPH14-BGR-BLK-KIT | Serialized |  |  |  | 1
[6 empty] | SAM-GS24P-1004-KIT | Serialized |  |  |  | 1
[6 empty] | SUR-SAM-1052 | Non-Serialized | 4 |  | 11

## copy of original matrix5.29 (hidden)
NEW AWS Cycle Count Truth Table
SERIALZED PARTS | [6 empty] | Impact on Inventory count THIS location |  | Impact on Inventory count OTHER location
Scenario | Discrepancy | Current Status | Serial number | ServiceBench Action(s) | Servicer Action (in report) | Updated Status | In Stock | Available | In Stock | Available | Notes | Agree on Logic (Y/N)
1 | Not Counted | In Stock | TCP3SPTOSDONTUSE333104 TCP3SPTOSDONTUSE333131 TCP3SPTOSDONTUSE333143 TCP3SPTOSDONTUSE333145 TCP3SPTOSDONTUSE333147 | 1. Change status to "Discrepancy" | Investigate | Discrepancy | Decrement | Decrement |  |  |  | Y
2 | Part Status Mismatch | Installed |  | – | Return Part | Installed | – | – |  |  |  | Change action to "Return through DOA/core process"
3 | Part Status Mismatch | DOA | TCPSRFSPRAPL121212143 TCPSRFSPRAPL121212134 TCPSRFSPRAPL121212130 TCPSRFSPRAPL121212126 | – | Return Part | DOA | – | – |  |  |  | Y
4 | Part Status Mismatch | Return | TCPAUTOAPL1093373335 TCPAUTOAPL1093373346 | – | Return Part | Return | – | – |  |  |  | Y
4.5 | Part Status Mismatch | Discrepancy | TCPSRFSPRAPL121212132 TCPSRFSPRAPL121212133 | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  |  | Y
5 | Wrong location | In Stock | TCPSRFSPRAPL121212138 | 1. Transfer part to this location | – | In Stock | Increment | Increment | Decrement | Decrement |  | Is the transfer perform by SB or user?
6 | Wrong location | Installed | 75412589 | – | Return Part | Installed | – | – | – | –
7 | Wrong location | DOA |  | – | Return Part | DOA | – | – | – | –
8 | Wrong location | Return |  | – | Return Part | Return | – | – | – | –
8.5 | Wrong location | Discrepancy | TCPSRFSPRAPL121212139 | 1. Transfer part to this location 2. Change status to "In Stock" | – | In Stock | Increment | Increment | – | – |  | Is the transfer perform by SB or user?
9 | Wrong location | Pending Receiving |  | 1. Receive Part at this location | – | In Stock | Increment | Increment | – | – |  | ? What is the impact for other location's pending receiving? How will their inventory be fixed or will it remain PR until manually updated?
10 | Not Received | Pending Receiving |  | 1. Receive Part | – | In Stock | Increment | Increment |  |  |  | Y
11 | Unrecognized | any |  | – | Return Part | no change | – | – |  |  | serial number pattern match | Do we have an example?
12 | Unrecognized | N/A |  | – | Return Part | no change | – | – |  |  | no pattern match | Is this what we consider as unknown or misscans today?
13 | Lost Part | Lost |  | – | Return Part | no change |  |  |  |  | consumable repair part | What's difference in 13/14 lost example?
14 | Lost Part | Lost |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | scheduable asset
NEW - 15 | Part Status Mismatch | Expected Return |  | – | Return Part | Expected Return | – | –
NEW - 16 | Status Mismatch | Removed | FVFZDAASLYWH | – | – | no change | – | – | – | – | Removed status used for MacBooks and Mifis. IT Asset team now manages this inventory. We don't want field to return these assets as they're no longer in inventory. | Change - do not return parts
NEW - 17 | Matched | Reserved | SEAOSAMGS22O9T180819 | – | – | no change | – | – | – | – |  | Y
NEW - 18 | Matched | In Stock |  | – | – | no change | – | – | – | – |  | Y
NEW - 19 | PART_USED | Lost - Cycle Count | SEAOSAMGS23O5L147606 | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
New - 20 | Part used | LOST_IN_TRANSIT_FROM_TLC |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
New - 21 | Part used | LOST_IN_TRANSIT_TO_TLC |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
New - 22 | Part used | LOST_THEFT |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
New - 23 | Part used | LOST_AUDIT |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
New - 24 | Part used | LOST_OTHER |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
New - 25 | Part used | LOST_CLOSED_LOCATION |  | 1. Change status to "In Stock" | – | In Stock | Increment | Increment |  |  | These are Finance terminal statuses after inventory is written out of DAX.
NEW - 26 | Not Counted | Reserved |  | 1. Change status to "Discrepancy" | Investigate | Discrepancy | Decrement | Decrement
NON-SERIALZED PARTS | [6 empty] | Impact on Inventory count THIS location |  | Impact on Inventory count OTHER location
Scenario | Discrepancy | Current Status |  | ServiceBench Action(s) | Servicer Action (in report) | Updated Status | In Stock | Available | In Stock | Available | Notes
| Quantity Under |  | IB-0727 | 1. Update quantity | – |  |  | –
2 | Quantity Over |  | MB-0727 | 1. Update quantity | – |  | – | –
3 | Not Received |  | IB-0727 | 1. Receive Part 2. Update Quantity | – |  | Increment | Increment
4 | Unrecognized |  |  | – | – |  | – | –
5 | Lost Part |  |  | 1. Change status to "In Stock" | – |  | Increment | Increment
| Date | Change in this version
v03 | 08.12.2018 | Added scenario 4.5 - to cover case of scan / Over for part in Discrepancy status at this location.
Added scenario 8.5 - to cover case of no match / Discrepancy at one location, followed by a scan / Over for same part at a dfferent location.
Added scenarios 13 and 14 - to cover case of parts in Lost status - both for consumable parts (13) and non-consumable "schedulable asset" parts (14)
v02 | 04.19.2018 | Clarified the 2 types of "unrecognized"
#11: serial number is known to SB, but at another SP, OR serial number is NOT known, but pattern matches Asurion serial number pattern.
#12: serial number is NOT known to SB, AND serial number does NOT match Asurion serial number pattern. ("UNKNOWN")
v03 | 02.09.2019 | Added rules for non-serialized parts

## Sheet2 (hidden)
Open
In Progress
Resolved

## Testing Locations
Program | Location Name | ServiceBench ID | Part Location Number | Notes
AT&T | Liberty Mobile - Santa Maria | 1170894219 | 1170894219
3PL | UNITED SMART TECH-RT Amarillo | 915619308 | SUR-700 | Office
AT&T | Liberty Mobile - Plaza del Sol | 1170895996 | 1170895996

## TCP Catergory (hidden)
Discrepancy | Result of Validation | TCP Action/Status | Category
Not Counted | Lost | Lost | Lost
Not Counted | Return | Return | No Action
Not Counted | Installed/Insalled | No Action | Gain
Not Counted | InStock | No Action | Exclude
Not Counted | Dead on Arrival | No Action | Duplicate
Location Variance
Matched | n/a | No Action | Overage
PART_USED | n/a | Overage
Status Mismatch | n/a | Overage
Incorrect Location | n/a | Overage
Return | n/a | Overage
Not Received | n/a | Overage
Not Counted | n/a | No Action
Over Counted | n/a | No Action
None Counted | n/a | No Action

## Test Cases
Scenario# or Matrix line | Description | UAT Status | Requested by | Initiated by | User | I want | So I can | Impacted teams | Notes/Questions | Exceptions/Impact | Legacy Picture | Next Gen Pictures | Recording Link | Recording Passcode
1 | Confirm user has access to Next Gen link |  | Gerri | Gerri | Field | click "Next Gen CC" | Start count | Field | Will users encounter any issues if they're not on VPN?
2 | Setup Service job email to receive copy of preview/final cycle count report | Confirmed | Gerri | Gerri | Field | Field to have access to edit,add or remove email addresses | Field to receive copy of preview/final cycle count report via email | Field | Current UI sends email SB Path: Jobs>Service Job Configuration> Manage locations>Service Job Emails> Parts and Inventory Email |  |  |  | https://asurion.zoom.us/rec/share/pOZNl4vl_ZhzSmXGUvBT2rdaOrvBKEoB_z8gzS78v2WsDCM1ECLCei3-g52CgwiM.USG6LGPyly_8otWp?startTime=1751984760000 | u!uX@48i
| Provider's access to complete counts for multiple locations |  | Gerri | Gerri | Field | Field to have ability to select location to start count. 1 - Location Name 2- Part location number 3 - Status 4 - Last Cycle Count date/time | Field know when last count was completed for each location under provider login | Field | Confirm with Mike if each location has separate logins or if multiple are one and account |  | #VALUE!
Remove | Summary view with skus/qtys/serials for reference missing /expected parts |  | Gerri | Gerri | Field | Summary tab to be visible in separate tab within the count | Reference missing parts quickly and expected skus/qtys instead of exiting screen and going back and forth to count page | Field | Legacy has this view. |  |  | #VALUE!
| Scan non-serialized part | Confirmed 7/8 |  |  |  | Message to state "Part scanned. Ensure quantity scanned is accurate before completing cycle count" | Field knows part was scanned | Field |  |  |  | #VALUE!
| Field misscannned non-serialized part and needs to correct/clear qty entered. | Confirmed 7/7 | Gerri | Gerri | Field | Ability to click 1- Decrement - UI to reduce qty by "1" 2 - Clear - UI to reduce total qty to "0" | Correct scanned qty | Field | Legacy has this function | If field is unable to edit qty, may result in incorrect update to inventory |  | #VALUE! | https://asurion.zoom.us/rec/share/_qbewdjfXTX5T3A_oSxC_ahXIekK0Wmrcsj6DCZduqVIo3cqSAvqehjKSr2A5ClV.7WRD5w7cZFZ5Xm9P
Future Enhancement | Verbiage change Error message when clicking Decrement | Enhancement on hold |  |  |  | Change Verbiage " Quantity scanned reduced by 1. Ensure quantity scanned is accurate before completing cycle count" | Field knows what changes are being made | Field
Future Enhancement | Verbiage change Error message when clicking Clear | Enhancement on hold |  |  |  | Error message to be RED and states " Quantity scanned was set to 0. Ensure quanity scanned is accurate before completing cycle count." | Field knows what changes are being made | Field
| Verbiage change Unexpected non-serialized sku scanned in count. |  | Gerri | Gerri | Field | Change verbiage "Unexpected part counted. Quantity will be incremented" | visually confirm part will be incremented into inventory | Field
| Scan a serial that was already counted | Confirmed | Gerri | Gerri | Field | Error message to be RED and states "Serial has already been scanned." | confirm part was already scanned | Field |  |  |  | #VALUE!
| Scan Matched serials | Confirmed | Gerri | Gerri | Field | Error message to be GREEN and states "Serial scanned. No updates required." | confirm part was scanned | Field |  |  |  | #VALUE!
Matrix #1 | Do not scan 2 serials - Not Counted |  |  |  |  | Serials to show Discrepancy status - Not Counted Updated Status - Discrepancy Action - Investigate
| UI scan sounds |  |  |  | Field | 1 - Error sound ( unknown, overages) | field can double check part scanned was correct or rescan part | Field | 7/8 - Confirmed duplicate scan has sounds.
| DOA and installed serials | Confirmed |  |  |  | Error message to be GREEN and states "The serial scanned will be returned at the end of this cycle count.." Action : Return through DOA/Core process | Field knows part needs to be returned. |  |  |  |  | #VALUE! |  | 8:40
Matrix 10 | Pending Receiving serials for correct location | Confirmed | Gerri | Gerri | Field | Error message to be GREEN and states "Pending receiving serial will be received at this location upon cycle count completion." | confirm part was scanned and inventory will be adjusted | Field |  |  |  | #VALUE!
Matrix 4.5 | Discrepancy serial from correct location | Confirmed | Gerri | Gerri | Field | Error message to be GREEN and states "Serial scanned. Will update to in stock at counting location." | confirm part was scanned and inventory will be adjusted | Field
| Unknown part - non serial format |  | Gerri | Gerri |  | Change Error message to be RED and states "This serial (X) number is not recognized. If you believe this is an error, please re-scan." |  | Field |  |  |  | #VALUE!
| Unknown part - serial format |  | Gerri | Gerri |  | Error message to be and RED states: The serial or part scanned is not recognized. Please return at the end of the cycle count. |  | Field
| Enter notes in preview screen 1 - character limitation 2 - enter notes on any/all lines | Confirmed 7/7 | Gerri | Gerri | Field | 1 - to enter notes and see the characters counted on screen 2- enter notes on any/all lines | Submit final count | Field | PRO: NextGen counts the characters for all notes and won't allow user to add more than 250 characters! :) No risk of field not being able to submit final count
| Notes added to discrepancies to be visibile in Preview screen | Confirmed 7/30 | Gerri | Gerri | Field | Column to be added to preview report as "Saved Notes" | field can ensure all notes required were entered correctly | Field
| Ability to export cycle count in preview report screen | issue with preview report name |  |  | Field | "Export Preview Report" button | field can review initial cycle count report before submitting final count. | Field | Mirrors final count template.
| Add warning message for User to confirm they want to submit final count. Mirror Legacy | Confirmed 7/8 |  |  | Field | Add warning message for User to confirm they want to submit final count. | Field is aware no changes can be made once a count is submitted | Field |  |  | #VALUE! | #VALUE!
| After clicking final report, message appears "Submitting final count… The final report will be emailed to the inventory manager. The final report will be emailed to the inventory manager." Confirm who will get email. Is this based on the SB configuration setup? Will final report be emailed to FIST mailbox?Asurion-SURAuditTeam@asurion.com |  |  |  |  | Change verbiage 1 - Remove duplicate sentence 2 - Ensure final report sent to FISt mailbox/field | 1 - 2 - FIST can consolidate files for reporting | Field | Confirmed email is being sent to email addresses in SB configuration setup 7/8 |  |  | #VALUE!
| Print Cycle count discrepancy label and packing slip | Confirmed 7/30 |  |  | Field | Ability to print discrepancy label and packing slip | search, pack and ship return items/discrepancies | Field
| Find and obtain cycle count discrepancy label for reprint RMA Portal |  |  |  | Field | Confirm field can access label and reprint as needed How will field know what is CCD vs. RMA PB vs. Core return? | ship return parts | Field
| Final count serial output shows correct format (xlsx file) |  | Gerri | Gerri | FIST,TCP | Serials to be complete in final count file | team can consolidate counts, add to reporting and use for store closure RMAs and research | FIST,TCP

## Demo
WI Step | Callouts for WIs | Scenario | Matrix # / | Testing Serial
Navigate to NextGen cycle count link
Select loction to complete count | Ensure correct location is selected
Inventory Cycle Count view | Describe different statuses 1 - Completed 2 - Cancelled 3 - In Progress
Summary view | Refer to the Summary view to confirm all parts are counted.
New page/ row function | Ability to to select amount of rows or page
Ability to cancel count
Start count
Do not scan 2 serials |  | Not Counted > Discrepancy | 1
Scan remaining serials |  | Matched > Instock Matched > Reserved | 18 17
Scan overage |  | Unrecognized > Discrepancy | 4.5 | 1.2147e+17
Scan overage |  | Unrecognized > LOST | 44 | 2.1835e+17
Scan overage |  | Unrecognized > Lost_Cycle_Count | 19 | 2.5554e+17
Scan overage |  | Unrecognized > Removed | 16 | 2.2894e+17
Scan overage |  | Unrecongized > Installed | 2 | 86255621405862208
Scan overage |  | Not Received > Pending Receiving | 10 | 1.6111e+17
Scan expected non-serialized SKU |  | Matched
Edit non-serialized QTY | Describe ability to click : 1 - Decrement - reduce qty by "1" 2 - Clear - reduce total qty to "0"
Scan non-serialized SKU (Overage) |  |  |  | SAM12535
Scan unknown part (mis-scan) | serial number pattern match - unknowns (mis scans) or Greater than 10 characters | Unrecognized> | 11 | %jg;aog80ho4340380h0
Scan unknown part (mis-scan) | no pattern match - unknowns (mis scans) Less than 10 characters | Unrecognized> | 12 | %9agwoe2
Sort skus in counting screen | Ability to sort SKUs
Go back to summary view
Proceed to preview UI view | Ability to sort
Add notes to not counted serials | Reminder to save notes 250 character limit
Submit final count | Ability to submit final count or option to return to count
Cycle count discrepancy returns | Need to click print to proceed
Print packing & shipping label in UI | Ensure the shipping label is fully printed. Do not cut off the label. Ensure the packing slip in included in the package.
Find packing slip & shipping label in RMA portal | Note: This is a backup option 1 - How to identify cycle count discrepancy return from RMA, or RM return. "CYC#"

## Sheet1 (hidden)
Current / NEW | Description | Details | Pictures
Current | update SB logic to correctly return and increment/decrement parts (already in progress with Raghu) | See truth table. Started in 2024
Current | Cycle Count files – today we only get them via email and cannot access via SB | Ability to export CC files directly from SB Ability to export multiple CC files at the store or region level Ability to export consolidated CC files by date range and location/program - today we access files from Mailbox (emails) TCP team consolidates all cycle counts and create weekly/ EoM reporting for compliance and shrink metrics. | #VALUE!
Current | Cycle Count entering qty for tools by hand after they scan the barcode instead of SKU barcode labels | they have to scan each time even when they have 5-100 of the same tool like the black stick and other little stuff. - misscans lead to discrepancies.
Current | Cycle Count scanning and discrepancies, add some product description so they know what to go look for | older models - identify parts Summary Preview
Current | Cycle Count duplicates (BUG?) scanning says duplicate serial even at the very first scan, 5ish locations has this happen every time. | TCP team must manually remove duplicate serial from final cycle count report | #VALUE!
Current | Update logic to not signal return for instock parts Current logic issue - SB instructing location to return instock parts. Update to leave part instock. No return needed. | Location counted 4 parts last month and SB asked them to RETURN the parts during their cycle count, but the part shows as in stock. This is impacting their inventory as they returned the inventory using the cycle count discrepancy label, but the inventory wasn’t decremented. | #VALUE!
Current | Update Current history to show all parts statuses SB isn't showing history of part installed etc. from a different location. | Other serials show all serial history in the current lines. Whether part was previously installed, lost etc. | #VALUE!
NEW | Notes Character Limitation - today locations aren't able to submit final counts if characters are over limit. Is there a limit in AWS? | Cycle count times out at 12AM. If count isn't completed, location needs to perform another count. Only SB team can manually fix issue if caught early. Sometimes the field didn't exceed character limit and SB wouldn't allow field to submit final cycle count.
NEW | Ability to export preview report at any time while cycle count is in progress | Location can check on progress and research serials at any time. SB only shows preview report within SB. No option to export. | #VALUE!
NEW | Final Cycle Count file - today SB automatically names the file. Mirror for new program | Today's file includes: SB ID,Location name, date and timestamp Our team can quickly find report in mailbox and determine when count was completed.
NEW | Skus in Summary to follow chronological order | Inventory at each location is sorted by sku types
NEW | Row Limitation - Ability to see all rows instead of selecting row page. | Keep row option. Add "See all rows" | #VALUE!
NEW | Log records of "unknown" parts and add pop up alert/message when scannning invalid parts. | Need visibilty to parts that were never in SB or shipped to location. FIST refers to these parts as unknowns or misscans. This is where field/tech is scanning the incorrect barcode. | #VALUE!
NEW | Cycle Count - Not counted parts during cycle count. Add tab for uncounted parts. | Today SB has a tab to show the which counts weren't counted. Helps locations search missing parts in one page instead of scrolling through all inventory pages. | #VALUE!
NEW | Do the final reports get emailed based on SB setup for RETURN emails? | Provider must enter their individual email address to receive final cycle count reports etc. Need to confirm if this will mirror the same logic. Field needs visibilty for final cycle count report to ensure overages are returned and discrepancies can be researched and found to reduce shrink. | #VALUE!
NEW | Cycle Count submission - today SB will show pop up message to confirm if location wants to submit cycle count. Mirror message and allow location to return to preview report screen. | If the location accidentally hits submit as it's setup now, may lead to invalid inventory report, recount, and/or manual inventory fix. ➔ If you accidentally click the SUBMIT FINAL COUNT button, a warning message will pop up. Click CANCEL to return to the Preview Report screen. ➔ Clicking SUBMIT FINAL COUNT and OK on the subsequent warning message will finalize the count and email the final file to the distribution list.
NEW | Non-serialized skus in final report - serial for non-serialized to show as "&nbsp;" Mirror today's output | Today's reports show non-serialized parts as "&nbsp;" to easily distinguish from true serialized parts. | #VALUE!
NEW | Automatically increment "lost" inventory into instock/available inventory for gains | Today, FIST Inventory intgrity team manually adjust previously "lost" inventory by flipping serials in SB to instock and adjusting DAX inventory. Removing manual step will result in updated inventory stocks for field, reduce returns and processing time for SUR team, remove additional cleanup steps for FIST/ Inventory Integrity team and result in gains or write in for the month to reduce overal shrink
NEW | NEW UI shows return action for field to know what needs to be: Investigated left on inventory rack etc. Need to review fill list of actions and adjust as needed during UAT testing | Field can easily route inventory back to rack or hold for returns instead of leaving "not available" inventory in location.
NEW | Confirm if field will be able to print "overages/returns" packling slip/ return shipping label from " RMA/Cycle Count Dashboard" | Today, field prints shipping label from dashboard to ship back excess inventory from final cycle count report. Serials are listed as "return" in Action (by servicer) column. Field print UPS label to drop off returns to UPS. Tracking # link direct field to UPS site to see shipping updates.

## . (hidden)
Location Name | Service Provider ID
UNITED SMART TECH-RT JACKSON | 915619308
UNITED SMART TECH-RT MONROE | 915619308
UNITED SMART TECH-RT BRYAN | 915619308
UNITED SMART TECH-RT ODESSA | 915619308
UNITED SMART TECH-RT ALEXANDRIA | 915619308
UNITED SMART TECH-RT MIDLAND | 915619308
UNITED SMART TECH-RT ABILENE | 915619308
UNITED SMART TECH-RT AMARILLO | 915619308
UNITED SMART TECH-RT SHERMAN | 915619308
UNITED SMART TECH- RT LUBBOCK | 915619308
UNITED SMART TECH-RT LAWTON | 915619308
UNITED SMART TECH-RT LAS CRUCES | 915619308
UNITED SMART TECH-RT SAN ANGELO | 915619308
UNITED SMART TECH-RT VICTORIA | 915619308
UNITED SMART TECH-RT JOPLIN | 915619308
UNITED SMART TECH-RT ARDMORE | 915619308